## Model
Product Management First Steps with Doug Winnie
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 2.7534e-14
CHG |  | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333
Actual % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 0
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Actual Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
This example model uses a 30-day sprint. Below, you can define the total capacity of your team and how much estimated completion and work effort are accomplished each day. Using the cream-colored cells above, replace the calculated cells with your actual burndown information.
Estimated % Complete per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work per Day |  | 3: 15

## Curved Model
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 99 | 99 | 99 | 99 | 98 | 97 | 96 | 94 | 92 | 90 | 87 | 84 | 81 | 77 | 73 | 69 | 64 | 59 | 54 | 48 | 42 | 36 | 29 | 22 | 15 | 9 | 4 | 0 | 0 | 0
CHG |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 6 | 5 | 4 | 0 | 0
Actual % Remaining | 100 | 100 | 100 | 100 | 100 | 99 | 98 | 97 | 95 | 93 | 91 | 88 | 85 | 82 | 78 | 74 | 70 | 65 | 60 | 55 | 49 | 43 | 37 | 30 | 23 | 16 | 10 | 5 | 1 | 1 | 0
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Actual Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
This example model uses a 30-day sprint, showing a curved model for the amount of progress in completion of features.
Estimated % Complete per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work per Day |  | 3: 15

## Good Burndown
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 2.7534e-14
CHG |  | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 5 | 0 | -10 | 5 | 5 | 5 | 5 | 10 | 10 | 5 | 0 | 0 | 0 | 5 | 0 | 0
Actual % Remaining | 100 | 100 | 100 | 100 | 95 | 90 | 85 | 80 | 70 | 60 | 50 | 45 | 45 | 45 | 45 | 40 | 40 | 50 | 45 | 40 | 35 | 30 | 20 | 10 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 10 | 12 | 15 | 17 | 12 | 15 | 15 | 12 | 16 | 17 | 15 | 10 | 10 | 5 | 5 | 20 | 30 | 10 | 15 | 10 | 7 | 5 | 8 | 9 | 7 | 6 | 9 | 8 | 7 | 6
Actual Work Effort | 0 | 10 | 22 | 37 | 54 | 66 | 81 | 96 | 108 | 124 | 141 | 156 | 166 | 176 | 181 | 186 | 206 | 236 | 246 | 261 | 271 | 278 | 283 | 291 | 300 | 307 | 313 | 322 | 330 | 337 | 343
This example model shows a good burndown where the work effort is below the estimate and features are completed before the end of the sprint.
Estimated % Complete per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work per Day |  | 3: 15

## Bad Burndown
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 2.7534e-14
CHG |  | 0 | 0 | 0 | 5 | 3 | 5 | 4 | 6 | 2 | 3 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 3 | 1 | 5 | 10 | 5 | 0 | 5
Actual % Remaining | 100 | 100 | 100 | 100 | 95 | 92 | 87 | 83 | 77 | 75 | 72 | 66 | 63 | 61 | 60 | 60 | 60 | 60 | 60 | 60 | 58 | 56 | 55 | 53 | 50 | 49 | 44 | 34 | 29 | 29 | 24
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 10 | 12 | 11 | 13 | 14 | 13 | 12 | 11 | 10 | 9 | 12 | 23 | 12 | 18 | 13 | 16 | 25 | 21 | 25 | 23 | 18 | 17 | 15 | 13 | 15 | 20 | 25 | 20 | 30 | 15
Actual Work Effort | 0 | 10 | 22 | 33 | 46 | 60 | 73 | 85 | 96 | 106 | 115 | 127 | 150 | 162 | 180 | 193 | 209 | 234 | 255 | 280 | 303 | 321 | 338 | 353 | 366 | 381 | 401 | 426 | 446 | 476 | 491
This example model shows a bad burndown where the work effort exceeds the estimate and features aren’t completed at the end of the sprint.
Estimated % Complete per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work per Day |  | 3: 15